Appendix  10

JOINT NORWEGIAN – RUSSIAN SCIENTIFIC RESEARCH PROGRAM ON LIVING MARINE RESOURCES IN 2004

###### Contents

1.	Planning and coordination of investigations and submitting of results	2

2.	Investigations on fish and shrimp stocks, including stock size, -structure, -distribution, -interactions and -ecology	2

3.	Investigations on Red King crab	15

4.	Fishing technology and selectivity of fishing gears	17

5.	Multispecies interactions in the Barents Sea	20

6.	Oceanographic investigations	20

7.	Monitoring of pollution levels in the Barents Sea	21

8.	Investigations on age and growth of fish	21

9.	Investigations on marine mammals	21

10.	Investigations on hydro-acoustic methodology	23

11.	Norwegian – Russian Symposium	24

12.	Catch volumes needed for investigations of marine resources and monitoring of the most important commercial species, as well as management tasks.	24

# Planning and coordination of investigations and submitting of results

This program contains the investigations to be carried out in 2004 by Norway and Russia within the frames of the bilateral cooperation between the Norwegian and the Russian parties.  The program is in accordance with the national research programmes. Planning, coordination, accomplishment of the investigations, exchange of specialists, data and results will be settled between the two institutes involved. Scientists and specialists from PINRO and IMR will meet in Kirkenes 15-17 March 2004, to discuss joint research programmes, results from surveys and investigations in 2003/2004 and to coordinate survey plans for the rest of 2004. Missing names on vessels and time periods for surveys in this report will be submitted, latest at the March meeting. Future plans for surveys and methodology for preparing biological and acoustic data will be discussed and coordinated. Urgent information according to surveys carried out before the meeting in March will be exchanged by correspondence.

In total, 3 reports have been issued in the Joint IMR-PINRO Report Series by 1. November 2003.

A preliminary program for the planned surveys and cooperation is presented below.

# Investigations on fish and shrimp stocks, including stock size, -structure, -distribution, -interactions and -ecology

IMR and PINRO will continue the co-operation on the monitoring of the most important commercial fish and shrimp stocks, according to the program listed below.  The work will also include continued co-operative research on:

- the stock structure of Northeast arctic cod, based on the joint research program 2003-2004.

- shrimp research as recommended by the ICES working group – with the objective to give recommendations that include the conservation of biodiversity

- by-catch of juvenile fish in the shrimp fishery

- species interactions between cod, herring, capelin and marine mammals

- investigations on Greenland halibut and Red King crab according to agreed joint research programs, 2002-2004

At its 30th session, the mixed Norwegian-Russian Fishery Commission decided to establish a three-year programme of joint Russian-Norwegian investigations of Greenland halibut stocks in 2002-2004. The content of the programme was agreed upon during the annual meeting between Russian and Norwegian scientists in March 2002, and the working schedule and distribution of responsibilities for individual components of the programme were agreed upon during a meeting in Tromsø 4-5 June 2002. A final report from the program is expected to be available during the 34th session of the Mixed Norwegian-Russian Fisheries Commission in 2005.

Data and results will be reported to the ICES Arctic Fisheries Working Group (AFWG) and Northern Pelagic and Blue Whiting Working Group (NPBWWG), and the Pandalus Working Group.

Norwegian investigations

| Nation: | Norway | Survey title: | Herring spawning area |
| --- | --- | --- | --- |
| Time period: | 28.02 – 07.03 | Vessel: | Håkon Mosby |
| Target species: | Herring | Secondary species: |  |
| Area: | Herring spawning areas off Norwegian coast from 58º-63ºN |
| Purpose: | Spawning migration and behaviour |
| Reported to: | Internal IMR survey report WGNPBW 2004 |

| Nation: | Norway | Survey title: | Bottom trawl survey Greenland halibut |
| --- | --- | --- | --- |
| Time period: | 15.03 – 04.04 | Vessel: | 1 hired trawler |
| Target species: | Greenland halibut Sebastes mentella | Secondary species: | S. marinus |
| Area: | 68ºN - 80ºN, 400 – 1500 meter depth |
| Purpose: | Bottom trawl survey with fixed trawl stations |
| Reported to: | Internal IMR survey report, ICES AFWG 2005 |

| Nation: | Norway | Survey title: | Tagging experiment Greenland halibut |
| --- | --- | --- | --- |
| Time period: | 15.03 – 04.04 | Vessel: | 1 hired longliner |
| Target species: | Greenland halibut | Secondary species: |  |
| Area: | 68ºN - 80ºN |
| Purpose: | Tagging survey and fishing experiments with vertical lines |
| Reported to: | Internal IMR survey report, ICES AFWG 2005 |

| Nation: | Norway | Survey title: | Bottom trawl survey Greenland halibut |
| --- | --- | --- | --- |
| Time period: | 15.03 – 11.04 | Vessel: | 1 hired trawler |
| Target species: | Greenland halibut Sebastes mentella | Secondary species: | S. marinus |
| Area: | 62ºN - 70ºN, 400 – 1500 meter depth + Bear Island channel |
| Purpose: | Bottom trawl survey with fixed trawl stations |
| Reported to: | Internal IMR survey report, ICES AFWG 2005 |

| Nation: | Norway | Survey title: | Cod spawning stock |
| --- | --- | --- | --- |
| Time period: | 18.03 – 07.04 | Vessel: | G.O. Sars |
| Target species: | Cod | Secondary species: | Haddock, Saithe |
| Area: | Spawning areas Troms - Lofoten |
| Purpose: | Acoustic survey of the North East Arctic Cod spawning stock. Investigations on maturity, fecundity and egg abundance. |
| Reported to: | Internal IMR survey report, ICES AFWG 2004 |

| Nation: | Norway | Survey title: | Herring larvae |
| --- | --- | --- | --- |
| Time period: | 20.03 – 12.04 | Vessel: | Håkon Mosby |
| Target species: | Herring | Secondary species: | Saithe |
| Area: | Norwegian shelf areas from Andenes to Karmøy |
| Purpose: | Distribution and abundance of herring larvae |
| Reported to: | Internal IMR survey report, WGNPBW 2004 |

| Nation: | Norway | Survey title: | Genetic mapping of cod on spawning areas |
| --- | --- | --- | --- |
| Time period: | 01.04 – 30.04 | Vessel: | Fangst |
| Target species: | Cod | Secondary species: |  |
| Area: | Fjord areas from Møre to Finnmark |
| Purpose: | Collection of genetic material (cooperation with Russian scientists, Ref corresponding Russian surveys in REZ) |
| Reported to: | Internal IMR survey report. PINRO |

| Nation: | Norway | Survey title: | Shrimp survey |
| --- | --- | --- | --- |
| Time period: | 15.04 – 06.05 | Vessel: | Jan Mayen |
| Target species: | Shrimp | Secondary species: | Various groundfish species |
| Area: | Barents Sea |
| Purpose: | Abundance and distribution of shrimp and benthos monitoring, hydrography |
| Reported to: | Internal IMR survey report, ICES AFWG 2005 |

| Nation: | Norway | Survey title: | Norwegian Sea survey |
| --- | --- | --- | --- |
| Time period: | 02.05 – 31.05 | Vessel: | G.O. Sars |
| Target species: | Herring, Blue whiting | Secondary species: | Zooplankton |
| Area: | Norwegian Sea |
| Purpose: | Acoustic abundance estimation of pelagic fish and plankton, hydrography |
| Reported to: | Internal IMR survey report, WGNPBW 2005, ICES PGSPFN 2005 |

| Nation: | Norway | Survey title: | Greenland halibut, trawl CPUE |
| --- | --- | --- | --- |
| Time period: | 20.05 – 31.05 | Vessel: | Two hired commercial trawlers |
| Target species: | Greenland halibut | Secondary species: |  |
| Area: | Troms – Spitsbergen 70º30’N - 73º30’N (6 days), 73º30’N - 76º00’N (5 days) |
| Purpose: | Abundance of Greenland halibut based on catch rates by commercial trawl (CPUE) |
| Reported to: | Internal IMR survey report, ICES AFWG 2004 and PINRO |

| Nation: | Norway | Survey title: | Bottom trawl survey Greenland halibut |
| --- | --- | --- | --- |
| Time period: | 02.08 – 24.08 | Vessel: | 1 hired trawler |
| Target species: | Greenland halibut Sebastes mentella | Secondary species: | S. marinus |
| Area: | 68ºN - 80ºN, 400 – 1500 meter depth |
| Purpose: | Bottom trawl survey with fixed trawl stations |
| Reported to: | Internal IMR survey report, ICES AFWG 2005 |

| Nation: | Norway | Survey title: | Bottom trawl survey Greenland halibut |
| --- | --- | --- | --- |
| Time period: | 02.08 – 29.08 | Vessel: | 1 hired trawler |
| Target species: | Greenland halibut Sebastes mentella | Secondary species: | S. marinus |
| Area: | 62ºN - 70ºN, 400 – 1500 meter depth + Bear Island channel |
| Purpose: | Bottom trawl survey with fixed trawl stations |
| Reported to: | Internal IMR survey report, ICES AFWG 2005 |

| Nation: | Norway | Survey title: | Tagging experiment Greenland halibut |
| --- | --- | --- | --- |
| Time period: | 08.08 – 22.08 | Vessel: | 1 hired longliner |
| Target species: | Greenland halibut | Secondary species: |  |
| Area: | 68ºN - 80ºN |
| Purpose: | Tagging survey and fishing experiments with vertical lines |
| Reported to: | Internal IMR survey report, ICES AFWG 2005 |

| Nation: | Norway | Survey title: | Tagging experiment Greenland halibut |
| --- | --- | --- | --- |
| Time period: | September | Vessel: | 1 hired longliner |
| Target species: | Greenland halibut | Secondary species: |  |
| Area: | 62ºN - 67ºN |
| Purpose: | Tagging survey and fishing experiments with vertical lines |
| Reported to: | Internal IMR survey report, ICES AFWG 2005 |

| Nation: | Norway | Survey title: | Fjord and coastal ecosystem survey |
| --- | --- | --- | --- |
| Time period: | 11.10 – 11.11 11.10 – 07.11 | Vessel: | Johan Hjort Jan Mayen |
| Target species: | Saithe, coastal cod, 0-group herring | Secondary species: | Haddock, Sebastes marinus |
| Area: | North Norwegian fjord and coastal areas from Varanger to Møre. |
| Purpose: | Acoustic and trawl abundance estimation of saithe, coastal cod and other groundfish species. Acoustic abundance estimation of 0-group herring. Environmental investigations |
| Reported to: | Internal IMR survey report, WBNPBW 2005, AFWG 2005 |

| Nation: | Norway | Survey title: | Bottom trawl survey Greenland halibut |
| --- | --- | --- | --- |
| Time period: | 15.11 – 05.12 | Vessel: | 1 hired trawler |
| Target species: | Greenland halibut Sebastes mentella | Secondary species: | S. marinus |
| Area: | 68ºN - 80ºN, 400 – 1500 meter depth |
| Purpose: | Bottom trawl survey with fixed trawl stations |
| Reported to: | Internal IMR survey report, ICES AFWG 2005 |

| Nation: | Norway | Survey title: | Tagging experiment Greenland halibut |
| --- | --- | --- | --- |
| Time period: | 15.11 – 05.12 | Vessel: | 1 hired longliner |
| Target species: | Greenland halibut | Secondary species: |  |
| Area: | 68ºN - 80ºN |
| Purpose: | Tagging survey and fishing experiments with vertical lines |
| Reported to: | Internal IMR survey report, ICES AFWG 2005 |

| Nation: | Norway | Survey title: | Bottom trawl survey Greenland halibut |
| --- | --- | --- | --- |
| Time period: | 15.11 – 12.12 | Vessel: | 1 hired trawler |
| Target species: | Greenland halibut Sebastes mentella | Secondary species: | S. marinus |
| Area: | 62ºN - 70ºN, 400 – 1500 meter depth + Bear Island channel |
| Purpose: | Bottom trawl survey with fixed trawl stations |
| Reported to: | Internal IMR survey report, ICES AFWG 2005 |

| Nation: | Norway | Survey title: | Tagging of herring |
| --- | --- | --- | --- |
| Time period: | 20.11 – 20.12 | Vessel: | Hired vessel |
| Target species: | Herring | Secondary species: |  |
| Area: | Nordland - Troms |
| Purpose: | Tagging of herring |
| Reported to: | Internal IMR survey report, WGNPBW 2005 |

| Nation: | Norway | Survey title: | Herring wintering area |
| --- | --- | --- | --- |
| Time period: | 01.12 – 20.12 | Vessel: | Johan Hjort |
| Target species: | Herring | Secondary species: |  |
| Area: | Vestfjorden and shelf areas outside Lofoten-Vesterålen |
| Purpose: | Acoustic abundance estimation of herring |
| Reported to: | Internal IMR survey report, WGNPBW 2005 |

| Nation: | Norway | Survey title: | Herring wintering area |
| --- | --- | --- | --- |
| Time period: | 01.12 – 20.12 | Vessel: | G. O. Sars |
| Target species: | Herring | Secondary species: |  |
| Area: | Vestfjorden |
| Purpose: | Methodological acoustic investigations herring |
| Reported to: | Internal IMR survey report |

Russian investigations

| Nation: | Russia | Survey title: | Greenland halibut |
| --- | --- | --- | --- |
| Time period: | 01.01-30.03 01.04-30.06 | Vessel: | 1 trawler 1 trawler |
| Target species: | Greenland halibut | Secondary species: | Cod, haddock, catfish and redfish |
| Area: | NEZ between 70° 00' - 73° 30' N |
| Purpose: | Investigation of stock condition, stock dynamics of CPUE, comparison in catchability "longline-trawl", tagging. Investigation of Greenland halibut distribution density in natural environment using video-acoustic equipment. |
| Reported to: | Internal survey report, ICES AFWG 2005 |

| Nation: | Russia | Survey title: | Greenland halibut |
| --- | --- | --- | --- |
| Time period: | 01.01-31.03 01.04-30.06 | Vessel: | 1 trawler 1 trawler |
| Target species: | Greenland halibut | Secondary species: | Cod, haddock, catfish and redfish |
| Area: | Area adjacent to Svalbard between 73° 30' - 76° 00' N |
| Purpose: | Investigation of stock condition, stock dynamics of CPUE, comparison in catchability "longline-trawl", tagging. Investigation of Greenland halibut distribution density in natural environment using video-acoustic equipment. |
| Reported to: | Internal survey report, ICES AFWG 2005 |

| Nation: | Russia | Survey title: | Greenland halibut |
| --- | --- | --- | --- |
| Time period: | 01.01-31.03 01.04-30.06 | Vessel: | 1 longliner 1 longliner |
| Target species: | Greenland halibut | Secondary species: | Cod, catfish, redfish, tusk and skates. |
| Area: | NEZ and area adjacent to Svalbard between 70° 00' - 76° 00' N |
| Purpose: | Investigation of stock condition, stock dynamics of CPUE, comparison in catchability "longline-trawl", tagging. |
| Reported to: | Internal survey report, ICES AFWG 2005 |

| Nation: | Russia | Survey title: | Cod, haddock |
| --- | --- | --- | --- |
| Time period: | 10.01-10.04 | Vessel: | 1 trawler |
| Target species: | Cod, haddock | Secondary species: | Catfish, redfish, flatfish and saithe |
| Area: | The Barents Sea, REZ and Grey Zone |
| Purpose: | Collection of data on distribution and biological condition during winter period and spawning, investigations of "predator-prey" interactions, stock structure using genetic methods, estimation of undersized fish by-catches. |
| Reported to: | Internal survey report, ICES AFWG 2005 |

| Nation: | Russia | Survey title: | Cod, haddock |
| --- | --- | --- | --- |
| Time period: | 15.01-31.03 | Vessel: | 4 trawlers |
| Target species: | Cod, haddock | Secondary species: | Catfish, flatfish, saithe, redfish and Greenland halibut |
| Area: | NEZ, Grey Zone, The Barents Sea Enclave and area adjacent to Svalbard |
| Purpose: | Collection of data on distribution and biological condition during winter and spawning, investigation of "predator-prey" interactions and other ecological interactions. |
| Reported to: | Internal survey report, ICES AFWG 2005 |

| Nation: | Russia | Survey title: | Distribution and migration of spawning and post-spawning herring |
| --- | --- | --- | --- |
| Time period: | 01.02-31.03 | Vessel: | 1 rented trawler |
| Target species: | herring | Secondary species: | Other pelagic species |
| Area: | The Norwegian Sea |
| Purpose: | Investigation of herring distribution, collection of data for stock assessment. |
| Reported to: | Internal survey report, ICES WGNPBW 2004 |

| Nation: | Russia | Survey title: | Cod, haddock |
| --- | --- | --- | --- |
| Time period: | 01.04-30.06 | Vessel: | 2 trawlers |
| Target species: | Cod, haddock | Secondary species: | Catfish, redfish, flatfish and saithe |
| Area: | The Barents Sea, REZ and Grey Zone |
| Purpose: | Collection of data on distribution and biological condition during feeding migrations, tagging of cod, investigations "predator-prey" interactions |
| Reported to: | Internal survey report, ICES AFWG 2005 |

| Nation: | Russia | Survey title: | Cod and haddock |
| --- | --- | --- | --- |
| Time period: | 01.04-30.06 | Vessel: | 4 trawlers |
| Target species: | Cod, haddock | Secondary species: | Catfish, flatfish, saithe, redfish and Greenland halibut |
| Area: | NEZ, Grey Zone, The Barents Sea Enclave and area adjacent to Svalbard |
| Purpose: | Collection of data on distribution and biological condition during feeding migrations, investigation of "predator-prey" interactions and population-genetic structure for cod. |
| Reported to: | Internal survey report, ICES AFWG 2005 |

| Nation: | Russia | Survey title: | Sebastes mentella |
| --- | --- | --- | --- |
| Time period: | 15.04-20.05 | Vessel: | 1 R/V |
| Target species: | Sebastes mentella | Secondary species: | Other demersal species |
| Area: | The Barents Sea including Norwegian Economic Zones and areas adjacent to Svalbard. |
| Purpose: | Assessment of abundance and biomass of redfish, oceanography |
| Reported to: | Internal survey report, ICES AFWG 2005 |

| Nation: | Russia | Survey title: | Shrimp and demersal fish |
| --- | --- | --- | --- |
| Time period: | 20.04-25.05 | Vessel: | R/V |
| Target species: | Shrimp and demersal fish | Secondary species: | Other demersal species |
| Area: | The Barents Sea including Russian Economic Zone and territorial waters |
| Purpose: | Assessment of abundance and distribution of shrimp |
| Reported to: | Internal survey report, ICES Pandalus WG 2004 |

| Nation: | Russia | Survey title: | Coast fjords survey of cod, haddock and saithe |
| --- | --- | --- | --- |
| Time period: | 01.05-30.06 | Vessel: | 2 R/V |
| Target species: | Haddock, cod, saithe | Secondary species: | Other demersal species |
| Area: | Russian territorial waters and the internal waters: coastal areas from Varangerfjord to Svjatoj Nos |
| Purpose: | Stock assessment of cod, haddock and saithe; collection of biological and genetic data for spawning cod |
| Reported to: | Internal survey report, ICES AFWG 2005 |

| Nation: | Russia | Survey title: | Cod, haddock |
| --- | --- | --- | --- |
| Time period: | 10.05-10.06 | Vessel: | 1 trawler |
| Target species: | Cod | Secondary species: | Catfish, flatfish and lumpsucker |
| Area: | Coastal areas between Varangerfjord and Svjatoj Nos. |
| Purpose: | Investigation of coastal cod distribution, stock structure using genetic methods, collection of biological data. |
| Reported to: | Internal survey report, ICES AFWG 2005 |

| Nation: | Russia | Survey title: | Inmature haddock, saithe and cod |
| --- | --- | --- | --- |
| Time period: | 20.05-20.06 | Vessel: | 1 R/V |
| Target species: | Haddock, saithe | Secondary species: | Other demersal species |
| Area: | The Barents Sea including Norwegian Economic Zone |
| Purpose: | Stock assessment of haddock, saithe, cod; distribution and CPUE |
| Reported to: | Internal survey report, ICES AFWG 2005 |

| Nation: | Russia | Survey title: | International herring survey in the Norwegian Sea |
| --- | --- | --- | --- |
| Time period: | 31.05-31.07 | Vessel: | R/V Fridtjof Nansen |
| Target species: | herring | Secondary species: | Other pelagic species |
| Area: | The Norwegian Sea |
| Purpose: | Acoustic stock survey |
| Reported to: | Internal survey report, ICES WGNPBW 2005, ICES WG for planning of pelagic fish surveys in the Norwegian Sea (PGSPFN) 2004. |

| Nation: | Russia | Survey title: | Cod, haddock |
| --- | --- | --- | --- |
| Time period: | 01.07-30.08 01.09-30.10 | Vessel: | 1 longliner 1 longliner |
| Target species: | Cod, haddock | Secondary species: | Catfish, skates, tusk |
| Area: | The Barents Sea, REZ and Grey Zone |
| Purpose: | Investigation of resources for longliners fleet, morpho-physiological characteristics and aggregations structure. |
| Reported to: | Internal survey report, ICES AFWG 2005 |

| Nation: | Russia | Survey title: | Cod and haddock |
| --- | --- | --- | --- |
| Time period: | 01.07-30.09 | Vessel: | 3 trawlers |
| Target species: | Cod, haddock | Secondary species: | Catfish, flatfish, saithe, redfish and Greenland halibut |
| Area: | NEZ, Grey Zone, The Barents Sea Enclave and area adjacent to Svalbard |
| Purpose: | Collection of data on distribution, abundance and morpho-biological condition during feeding, investigation of "predator-prey" interactions and influence of hydro and meteorological conditions on fish behaviour . |
| Reported to: | Internal survey report, ICES AFWG 2005 |

| Nation: | Russia | Survey title: | Greenland halibut |
| --- | --- | --- | --- |
| Time period: | 01.07-30.09 01.10-30.12 | Vessel: | 1 trawler 1 trawler |
| Target species: | Greenland halibut | Secondary species: | Cod, haddock, catfish and redfish |
| Area: | NEZ between 70° 00' - 73° 30' N |
| Purpose: | Investigation of stock condition, stock dynamics of CPUE, comparison in catchability "longline-trawl", tagging. Investigation of Greenland halibut distribution density in natural environment using video-acoustic equipment. |
| Reported to: | Internal survey report, ICES AFWG 2005 |

| Nation: | Russia | Survey title: | Greenland halibut |
| --- | --- | --- | --- |
| Time period: | 01.07-30.09 01.10-30.12 | Vessel: | 1 trawler 1 trawler |
| Target species: | Greenland halibut | Secondary species: | Cod, haddock, catfish and redfish |
| Area: | Area adjacent to Svalbard between 73° 30' - 76° 00' N |
| Purpose: | Investigation of stock condition, stock dynamics of CPUE, comparison in catchability "longline-trawl", tagging. Investigation of Greenland halibut distribution density in natural environment using video-acoustic equipment. |
| Reported to: | Internal survey report, ICES AFWG 2005 |

| Nation: | Russia | Survey title: | Greenland halibut |
| --- | --- | --- | --- |
| Time period: | 01.07-31.09 01.10-30.12 | Vessel: | 1 longliner 1 longliner |
| Target species: | Greenland halibut | Secondary species: | Cod, catfish, redfish, tusk and skates. |
| Area: | NEZ and area adjacent to Svalbard between 70° 00' - 76° 00' N. |
| Purpose: | Investigation of stock condition, stock dynamics of CPUE, comparison in catchability "longline-trawl", tagging. |
| Reported to: | Internal survey report, ICES AFWG 2005 |

| Nation: | Russia | Survey title: | Greenland halibut survey |
| --- | --- | --- | --- |
| Time period: | 01.07-31.09 | Vessel: | 1 trawler |
| Target species: | Greenland halibut | Secondary species: | Catfish, flatfish, saithe, redfish |
| Area: | REZ and Grey Zone. |
| Purpose: | Stock condition investigations, CPUE for stock assessment, tagging. |
| Reported to: | Internal survey report, ICES AFWG 2005 |

| Nation: | Russia | Survey title: | Cod, haddock |
| --- | --- | --- | --- |
| Time period: | 03.07-03.10 | Vessel: | 3 trawlers |
| Target species: | Cod, haddock | Secondary species: | Catfish, redfish, flatfish and saithe |
| Area: | The Barents Sea, REZ and Grey Zone |
| Purpose: | Collection of data on distribution and biological condition during feeding, investigation of "predator-prey" interactions, morpho-physiological characteristics, tagging of cod. |
| Reported to: | Internal survey report, ICES AFWG 2005 |

| Nation: | Russia | Survey title: | Cod, haddock |
| --- | --- | --- | --- |
| Time period: | 10.07-20.08 | Vessel: | 1 trawler |
| Target species: | Cod | Secondary species: | Catfish, flatfish and lumpsucker |
| Area: | Coastal areas between Varangerfjord and Svjatoj Nos. |
| Purpose: | Investigation of coastal cod distribution, stock structure using genetic methods, collection of biological data. |
| Reported to: | Internal survey report, ICES AFWG 2005 |

| Nation: | Russia | Survey title: | Shrimp and demersal fish |
| --- | --- | --- | --- |
| Time period: | 01.08-20.08 | Vessel: | R/V |
| Target species: | Shrimp and demersal fish | Secondary species: |  |
| Area: | Area adjacent to Svalbard |
| Purpose: | Assessment of abundance and distribution of shrimp (Proposed as joint survey) |
| Reported to: | Internal survey report, ICES Pandalus WG 2004 |

| Nation: | Russia | Survey title: | Distribution and migration of feeding aggregations of herring |
| --- | --- | --- | --- |
| Time period: | 15.08-30.09 | Vessel: | 1 rented trawler |
| Target species: | herring | Secondary species: | Blue whiting and mackerel |
| Area: | The Norwegian Sea |
| Purpose: | Mapping of herring feeding aggregations distribution. |
| Reported to: | Internal survey report, ICES WGNPBW 2005 |

| Nation: | Russia | Survey title: | Complex aerial survey with ecosystem approach elements |
| --- | --- | --- | --- |
| Time period: | 01.09-25.09 | Vessel: | Airborne laboratory An-26 Arktika |
| Target species: | Capelin, polar cod | Secondary species: | Marine mammals, birds, chlorophyll, zooplankton, oceanographic parameters on the sea surface |
| Area: | The Barents Sea |
| Purpose: | Distribution assessment of capelin and polar cod, marine mammals and birds, investigation of oceanographic parameters on the sea surface as well as identification of areas with high bioproduction. |
| Reported to: | Joint IMR/PINRO Report Series |

| Nation: | Russia | Survey title: | Cod, haddock |
| --- | --- | --- | --- |
| Time period: | 30.09-30.12 | Vessel: | 1 trawler |
| Target species: | Cod, haddock | Secondary species: | Catfish, redfish, flatfish and saithe |
| Area: | The Barents Sea, REZ and Grey Zone |
| Purpose: | Collection of data on distribution and biological condition during winter and feeding migrations, investigation of "predator-prey" interactions, stock structure using genetic methods. |
| Reported to: | Internal survey report, ICES AFWG 2005 |

| Nation: | Russia | Survey title: | Cod, haddock |
| --- | --- | --- | --- |
| Time period: | 01.10-31.12 | Vessel: | 5 trawlers |
| Target species: | Cod, haddock | Secondary species: | Catfish, flatfish, saithe, redfish and Greenland halibut |
| Area: | NEZ, Grey Zone, The Barents Sea Enclave and area adjacent to Svalbard |
| Purpose: | Collection of data on distribution and biological condition during winter and spawning migrations, investigation of "predator-prey" interactions; estimation of fish condition for winter period and spawning. |
| Reported to: | Internal survey report, ICES AFWG 2005 |

| Nation: | Russia | Survey title: | Multispecies demersal fish survey |
| --- | --- | --- | --- |
| Time period: | 15.10-31.12 15.10-31.12 | Vessel: | R/V Fridtjof Nansen 1 R/V |
| Target species: | Cod, haddock, Greenland halibut | Secondary species: | Catfish, redfish, flatfish and saithe |
| Area: | The Barents Sea including Norwegian and Russian Economic Zones and areas adjacent to Svalbard. |
| Purpose: | Assessment of cod, haddock and other demersal species stocks, “predator-prey” relation, oceanography |
| Reported to: | ICES AFWG 2005 |

| Nation: | Russia | Survey title: | Greenland halibut survey |
| --- | --- | --- | --- |
| Time period: | 16.10-15.11 | Vessel: | 1 R/V |
| Target species: | Greenland halibut | Secondary species: | Cod, haddock, catfish, redfish |
| Area: | The Norwegian Sea and areas adjacent to Svalbard. |
| Purpose: | Assessment of distribution and abundance. |
| Reported to: | Internal survey report, ICES AFWG 2005 |

| Nation: | Russia | Survey title: | Complex aerial survey with ecosystem approach elements in the framework of investigations of distribution and biomass assessment of feeding mackerel |
| --- | --- | --- | --- |
| Time period: | 25.06-05.08 | Vessel: | Airborne laboratory An-26 Arktika |
| Target species: | Mackerel | Secondary species: | Herring, blue whiting, sea mammals |
| Area: | The Norwegian Sea |
| Purpose: | Distribution and biomass assessment of feeding mackerel, abundance and distribution of marine mammals and birds, data on environment conditions on the sea surface, including identification of areas with high bioproduction. |
| Reported to: | Internal survey report, ICES WGNPBW 2005 |

Joint investigations

| Nation: | Norway/Russia | Survey title: | Joint Winter Survey |
| --- | --- | --- | --- |
| Time period: | 31.01 – 09.03 31.01 – 15.03 February (14d) 29.01 – 29.02 20.01 – 05.03 15.02 – 10.03 | Vessel: | G.O. Sars Johan Hjort Hired Norwegian vessels Russian R/V R/V Fridtjof Nansen Hired Russian Trawler |
| Target species: | Cod, Haddock | Secondary species: | Capelin, herring, Sebastes mentella, S. marinus, Gr. halibut |
| Area: | Barents Sea including NEZ and REZ |
| Purpose: | Abundance and distribution of demersal fish and capelin. Multi-species interactions with focus on the diet of cod, hydrography, plankton |
| Reported to: | Joint IMR/PINRO Report Series and ICES AFWG 2004 |

| Nation: | Norway/Russia | Survey title: | Joint blue whiting spawning area survey |
| --- | --- | --- | --- |
| Time period: | 18.03 – 19.04 10.03 – 05.05 | Vessel: | Johan Hjort R/V Fridtjof Nansen |
| Target species: | Blue whiting | Secondary species: | Other pelagic species |
| Area: | West of the British Isles |
| Purpose: | Abundance estimation and distribution of spawning blue whiting, hydrography, plankton |
| Reported to: | Internal IMR and PINRO survey reports, WGNPBW 2004 |

| Nation: | Norway/Russia | Survey title: | Joint capelin larvae and young herring survey |
| --- | --- | --- | --- |
| Time period: | 07.06 – 30.06 15.05 – 30.05 | Vessel: | Håkon Mosby R/V Fridtjof Nansen |
| Target species: | Capelin, Herring | Secondary species: |  |
| Area: | Southern Barents Sea (including NEZ and REZ) |
| Purpose: | Abundance and distribution of capelin larvae and young herring, hydrography, plankton |
| Reported to: | IMR-PINRO report series, WGNPBW 2005. |

| Nation: | Norway/Russia | Survey title: | Joint ecosystem survey, autumn |
| --- | --- | --- | --- |
| Time period: | 01.08 – 10.10 02.08 – 10.09 10.08 – 09.10 | Vessel: | Johan Hjort Jan Mayen R/V Fridtjof Nansen |
| Target species: | Greenland halibut, Redfish, Shrimp, Herring, Capelin, 0-group various species | Secondary species: | Cod, Haddock, Polar cod |
| Area: | Norwegian Sea – Svalbard – Barents Sea |
| Purpose: | Abundance and distribution of Greenland halibut (including juveniles north and east of Spitsbergen), Sebastes mentella, S. marinus, shrimp, herring, capelin, polar cod, 0-group of various species. Hydrography, plankton, sea mammals, seabirds, multi-species interactions |
| Reported to: | Joint IMR/PINRO survey report, ICES AFWG 2005, ICES ACFM autumn meeting 2004 |

# Investigations on Red King crab

Investigations on the Red King crab (Paralithodes camtschaticus) of the Barents Sea during 2004, in the framework of the joint program.

A symposium on the Red King Crab as an introduced species was arranged in Tromsø in June 2003.  Proceedings from the symposium will be published in the Joint IMR/PINRO Report Series.

The Parties have carried out or initiated research in all main topics of the Joint research program (see protocol of the joint scientist meeting in March 2002), except for topic 4; Improvement of methods for stock assessment and calibration of survey methods).

To enhance the research on the Red King Crab the Parties agreed to include the following topics to the joint programme: population structure (revealed by genetic, morphology or/and reproductive unit studies, in addition to migration and larvae drift investigations). The report on the joint Norwegian-Russian research programme of red king crab will be presented at the 34th session of the Joint Norwegian-Russian Fishery Commission in 2005.

As a part of the joint programme the Norwegian Party intend to arrange a Norwegian – Russian symposium in October 2004, to highlight new scientific knowledge on the Red King Crab in the Barents Sea. However, such an arrangement requires funding. Title and details for the symposium will be announced later.

### Norwegian investigations

| Nation: | Norway | Survey title: | Red King crab survey |
| --- | --- | --- | --- |
| Time period: | 23.08 – 11.09 | Vessel: | Johan Ruud |
| Target species: | Red King crab | Secondary species: |  |
| Area: | Fjords in Finnmark |
| Purpose: | Abundance estimation and ecological investigations |
| Reported to: | Internal IMR survey report. PINRO |

### Russian survey:

| Nation: | Russia | Survey title: | Red king crab |
| --- | --- | --- | --- |
| Time period: | 05.04-05.05 | Vessel: | 1 trawler |
| Target species: | Red king crab | Secondary species: |  |
| Area: | Russian Economic Zone and territorial waters |
| Purpose: | Study of Red King crab during spawning. Study of crab larvae, juveniles and benthos, tagging. |
| Reported to: | PINRO, IMR |

| Nation: | Russia | Survey title: | Red king crab |
| --- | --- | --- | --- |
| Time period: | 15.08-15.09 | Vessel: | 1 trawler |
| Target species: | Red king crab | Secondary species: |  |
| Area: | Russian Economic Zone and territorial waters |
| Purpose: | Red king crab distribution, stock assessment, tagging. |
| Reported to: | PINRO, IMR |

| Nation: | Russia | Survey title: | Red king crab |
| --- | --- | --- | --- |
| Time period: | 01.07.-15.12 | Vessel: | 2 vessels |
| Target species: | Red king crab | Secondary species: |  |
| Area: | Russian Economic Zone and territorial waters |
| Purpose: | Collection of data for experimental work on fattening of crab prerecruits, physiologic condition assessment of legal sized males. |
| Reported to: | PINRO, VNIRO, IMR |

| Nation: | Russia | Survey title: | Red king crab |
| --- | --- | --- | --- |
| Time period: | 01.04.-30.12 | Vessel: | 1 vessel |
| Target species: | Red king crab | Secondary species: |  |
| Area: | Russian territorial waters |
| Purpose: | Ecosystem investigations, distribution, biology and estimation of crab effect on the local ecosystems. |
| Reported to: | PINRO, VNIRO, IMR |

| Nation: | Russia | Survey title: | Red king crab |
| --- | --- | --- | --- |
| Time period: | 01.01-28.02 01.09-31.12 | Vessel: | 5 vessels 5 vessels |
| Target species: | Red king crab | Secondary species: |  |
| Area: | Russian Economic zone and territorial waters |
| Purpose: | Collection of data on CPUE, investigations of biology, abundance dynamic, migration patterns and interactions with local ecosystem species. |
| Reported to: | PINRO, IMR |

| Nation: | Russia | Survey title: | Benthos |
| --- | --- | --- | --- |
| Time period: | 01.06-31.07 | Vessel: | 1 R/V |
| Target species: | Macro-zoobenthos | Secondary species: | Macrozoobenthos |
| Area: | Russian Economic Zone and territorial waters |
| Purpose: | Mapping and assessment of zoobenthos |
| Reported to: | PINRO, IMR |

# Fishing technology and selectivity of fishing gears

Norwegian investigations:

| Nation: | Norway | Survey title: | Live fish technology for small coastal vessels |
| --- | --- | --- | --- |
| Time period: | 10.03 – 07.04 | Vessel: | Hired vessel |
| Target species: | Groundfish | Secondary species: |  |
| Area: | Vesterålen |
| Purpose: | Live fish technology for small coastal vessels |
| Reported to: | Internal IMR survey report |

| Nation: | Norway | Survey title: | Development of scientific sampling trawl |
| --- | --- | --- | --- |
| Time period: | 13.04 – 29.04 | Vessel: | G.O. Sars |
| Target species: | Groundfish | Secondary species: |  |
| Area: | Barents Sea |
| Purpose: | Development of scientific sampling trawl |
| Reported to: | Internal IMR survey report |

| Nation: | Norway | Survey title: | Survival during high fishing intensity |
| --- | --- | --- | --- |
| Time period: | 13.04 – 10.05 | Vessel: | 5 hired vessels |
| Target species: | Cod | Secondary species: | Groundfish species |
| Area: | Northern Troms |
| Purpose: | Survival during high fishing intensity |
| Reported to: | Internal IMR survey report |

| Nation: | Norway | Survey title: | Trials with floated fish pots |
| --- | --- | --- | --- |
| Time period: | 14.04 –26.04 | Vessel: | Hired Vessel |
| Target species: | Groundfish | Secondary species: |  |
| Area: | Coast of Finnmark |
| Purpose: | Trials with floated fish pots |
| Reported to: | Internal IMR survey report |

| Nation: | Norway | Survey title: | Trials with new designed cod trawl |
| --- | --- | --- | --- |
| Time period: | 14.04 –30.04 | Vessel: | Hired Vessel |
| Target species: | Cod, Haddock | Secondary species: |  |
| Area: | Barents Sea |
| Purpose: | Trials with new designed cod trawl |
| Reported to: | Internal IMR survey report |

| Nation: | Norway | Survey title: | Selectivity for lumpsucker in norsel gillnets |
| --- | --- | --- | --- |
| Time period: | 01.05 – 15.06 | Vessel: | 2 hired vessels |
| Target species: | Lumpsucker | Secondary species: |  |
| Area: | Coast of Finnmark |
| Purpose: | Study the usefulness of norsel gillnets for catching lumpsucker |
| Reported to: | Internal IMR survey report |

| Nation: | Norway | Survey title: | Behaviour of king crab in trawl |
| --- | --- | --- | --- |
| Time period: | 20.06 – 03.07 | Vessel: | Hired vessel |
| Target species: | Red King crab | Secondary species: |  |
| Area: | Finnmark |
| Purpose: | Behaviour of king crab in trawl |
| Reported to: | Internal IMR survey report |

| Nation: | Norway | Survey title: | Escapement under trawl |
| --- | --- | --- | --- |
| Time period: | 02.08 – 23.08 | Vessel: | Hired vessel |
| Target species: | Groundfish | Secondary species: |  |
| Area: | Barents Sea |
| Purpose: | Escapement under trawl |
| Reported to: | Internal IMR survey report |

| Nation: | Norway | Survey title: | Instrument and gear development for Danish seine |
| --- | --- | --- | --- |
| Time period: | 15.08 – 11.09 | Vessel: | Hired Vessel |
| Target species: | Demersal species | Secondary species: |  |
| Area: | Vest coast of Finnmark |
| Purpose: | Instrument and gear development for Danish seine |
| Reported to: | Internal IMR survey report |

| Nation: | Norway | Survey title: | Grid in herring trawl |
| --- | --- | --- | --- |
| Time period: | 10.11 – 28.11 | Vessel: | Hired vessel |
| Target species: | Herring, Saithe, Cod | Secondary species: |  |
| Area: | Vestfjorden |
| Purpose: | Grid in herring trawl |
| Reported to: | Internal IMR survey report |

| Nation: | Norway | Survey title: | Development of scientific sampling trawl |
| --- | --- | --- | --- |
| Time period: | 16.11 – 30.11 | Vessel: | G.O. Sars |
| Target species: |  | Secondary species: |  |
| Area: | Barents Sea |
| Purpose: | Development of scientific sampling trawl |
| Reported to: | Internal IMR survey report |

Russian investigations:

| Nation: | Russia | Survey title: | Cod, haddock |
| --- | --- | --- | --- |
| Time period: | 01.07-01.08 | Vessel: | 1 trawler |
| Target species: | Cod, haddock | Secondary species: | Other demersal species |
| Area: | The Barents Sea |
| Purpose: | Collection of data for scientific justification of regulation measures for cod and haddock fishery. Investigation of population and genetic structure of cod. |
| Reported to: | Internal survey report, ICES AFWG 2005 |

| Nation: | Russia | Survey title: | Selectivity of trawl and longline |
| --- | --- | --- | --- |
| Time period: | July-September | Vessel: | 1 longliner 1 trawler |
| Target species: | Greenland halibut | Secondary species: | Other demersal species |
| Area: | The Barents Sea, NEZ and Svalbard |
| Purpose: | Comparison fishing "trawl-longline". |
| Reported to: | Internal survey report, ICES AFWG 2005 |

| Nation: | Russia | Survey title: | Selectivity of trawl |
| --- | --- | --- | --- |
| Time period: | March-June July-December | Vessel: | 1 longliner 1 trawler |
| Target species: | Cod, haddock | Secondary species: | Other demersal species |
| Area: | The Barents Sea, Svalbard |
| Purpose: | Estimate efficiency of implementation of soft sorting systems in comparison with systems based on grids during fishing of cod and haddock. Mesh size in trawl bag is 135 – 155 mm. |
| Reported to: | Internal survey report |

# Multispecies interactions in the Barents Sea

The parties will:

- Continue work to establish a joint Norwegian-Russian database on stomach content of marine organism, including sea mammals, in the Barents Sea;

- Continue work to exchange biological data and data on fisheries for multispecies modelling;

- Continue work on multispecies modelling;

- Agree on a program for exchange of scientists;

- Establish a fundament for including marine mammals in the multispecies models for the population dynamics of the most important commercial species in the Barents Sea;

- Consider the possibility to use plankton data in the Barents Sea multispecies models.

The points above will be discussed at the scientific meeting in March 2004.

Multispecies interactions will be studied on several surveys listed under chapter 2 and 9.

# Oceanographic investigations

Oceanographic investigations will continue in the Barents Sea and Norwegian Sea in accordance with the existing international, bilateral and national programmes. Some surveys dedicated to oceanographic investigations are listed below. Such investigations will also be an integrated part of most of the surveys listed under chapter 2. Data on temperature and salinity from the joint investigations will be presented at the scientific meeting in March 2004. The data will be exchanged after correction and quality assurance.

Norwegian investigations:

| Nation: | Norway | Survey title: | Oceanographic sections |
| --- | --- | --- | --- |
| Time period: | 18.01 –29.01 | Vessel: | Johan Hjort |
| Target species: |  | Secondary species: |  |
| Area: | Norwegian Sea - Barents Sea |
| Purpose: | Svinøy, Gimsøy, Fugløya-Bear Island, Vardø-N |
| Reported to: | Internal IMR survey report |

| Nation: | Norway | Survey title: | Oceanographic sections |
| --- | --- | --- | --- |
| Time period: | 14.03 –18.03 | Vessel: | G.O. Sars |
| Target species: |  | Secondary species: |  |
| Area: | Barents Sea |
| Purpose: | Fugløya-Bear Island, Vardø-N |
| Reported to: | Internal IMR survey report |

| Nation: | Norway | Survey title: | Oceanographic sections |
| --- | --- | --- | --- |
| Time period: | 08.04 –12.04 | Vessel: | G.O. Sars |
| Target species: |  | Secondary species: |  |
| Area: | Norwegian Sea |
| Purpose: | Gimsøy NW |
| Reported to: | Internal IMR survey report |

| Nation: | Norway | Survey title: | Oceanographic investigations |
| --- | --- | --- | --- |
| Time period: | 13.06 –06.07 | Vessel: | Johan Hjort |
| Target species: |  | Secondary species: |  |
| Area: | Norwegian Sea - Barents Sea |
| Purpose: | Gimsøy NW, Bear Island West, Fugløya – Bear Island |
| Reported to: | Internal IMR survey report |

# Monitoring of pollution levels in the Barents Sea

PINRO and IMR will continue to monitor pollution levels in accordance with national programmes. Scientists from PINRO and IMR will discuss and exchange scientific information during the meeting in March 2004. The investigations are based on material collected during the surveys in the Barents Sea.

# Investigations on age and growth of fish

The cooperation between PINRO and IMR to establish an international database on length-at-age and weight-at-age of fish from scientific surveys and commercial catches will continue. This also includes commercial fisheries catch statistics archived at PINRO and IMR.

The exchange of age reading specialists and material will continue in 2004 according to established routines. In 2004, there will be one meeting of age reading specialists on cod, haddock and Greenland halibut in spring in Murmansk. Exact timing of the meeting will be decided by correspondence.

# Investigations on marine mammals

Studies of the biology and ecology of the harp seal is planned during the commercial hunt in the Southeastern Barents Sea. Furthermore biological and ecological studies of harp seals will be conducted in open waters of the Barents Sea during summer. Monitoring of minke whale diets will be conducted in the North Sea, the Norwegian Sea and the coast of Finnmark, preferably also in REZ if Russian authorities give permission. Abundance estimation surveys of minke whales will be conducted in the North Sea and the Norwegian Sea. Photoidentification studies of Humpback whales will be performed in the Barents Sea. Telemetric and ecological investigations of dolphins will be carried out in May-June in North Sea, Norwegian Sea and the Barents Sea. In 2004 increased effort will be spent on abundance estimation of grey and harbour seals on the Norwegian coast. Also ecological studies of grey seals will be conducted.

Norwegian investigations:

| Nation: | Norway | Survey title: | Grey seal survey |
| --- | --- | --- | --- |
| Time period: | 23.02-05.03 | Vessel: | Hired vessel |
| Target species: | Grey seal | Secondary species: |  |
| Area: | Norwegian coast from Vega to Lofoten |
| Purpose: | Ecological studies of grey seals |
| Reported to: | Internal IMR survey report, ICES, NAMMCO |

| Nation: | Norway | Survey title: | Harp seal sampling |
| --- | --- | --- | --- |
| Time period: | 25.03-01.05 | Vessel: | Commercial vessel |
| Target species: | Harp seal | Secondary species: |  |
| Area: | Southeastern Barents Sea |
| Purpose: | Biological studies of harp seals |
| Reported to: | Internal IMR survey report, ICES, NAMMCO |

| Nation: | Norway | Survey title: | Dolphin survey |
| --- | --- | --- | --- |
| Time period: | 01.05-11.06 | Vessel: | Hired vessel |
| Target species: | Dolphins | Secondary species: |  |
| Area: | North Sea, Norwegian Sea and Barents Sea |
| Purpose: | Telemetric and ecological studies of dolphins |
| Reported to: | Internal IMR survey report, ICES, NAMMCO, IWC |

| Nation: | Norway | Survey title: | Minke whale survey |
| --- | --- | --- | --- |
| Time period: | 15.05-15.06 | Vessel: | 4 hired Vessels |
| Target species: | Minke whale | Secondary species: |  |
| Area: | Norwegian Sea, North Sea, coast of Finnmark. |
| Purpose: | Biological sampling of minke whales. |
| Reported to: | Internal IMR survey report HI, IWC, ICES, NAMMCO |

| Nation: | Norway | Survey title: | Minke whale survey |
| --- | --- | --- | --- |
| Time period: | 28.06-08.08 | Vessel: | Hired Vessel |
| Target species: | Minke whale | Secondary species: |  |
| Area: | North Sea and Norwegian Sea |
| Purpose: | Counting program for estimation of minke whales in the North East Atlantic area. |
| Reported to: | Internal IMR survey report HI, IWC, ICES, NAMMCO |

| Nation: | Norway | Survey title: | Humpback whale survey |
| --- | --- | --- | --- |
| Time period: | 01.09-21.09 | Vessel: | Hired Vessel |
| Target species: | Humpback whale | Secondary species: |  |
| Area: | Norwegian and Barents Seas |
| Purpose: | Photoidentification of humpback whales. |
| Reported to: | Internal IMR survey report HI, IWC, ICES, NAMMCO |

Joint investigations:

| Nation: | Norway/Russia | Survey title: | Scientific whaling |
| --- | --- | --- | --- |
| Time period: | May-June | Vessel: | Commercial vessels |
| Target species: | Minke whale | Secondary species: |  |
| Area: | Murman coast |
| Purpose: | Biological and ecological investigations of minke whales. |
| Reported to: | Internal IMR survey report, IWC, ICES, NAMMCO, PINRO, SevPINRO |

| Nation: | Norway/Russia | Survey title: | Harp seal survey |
| --- | --- | --- | --- |
| Time period: | 01.06 – 01.08 | Vessel: | Two hired vessels (one Norwegian and one Russian) |
| Target species: | Harp seal | Secondary species: |  |
| Area: | Barents Sea |
| Purpose: | Ecological studies of harp seals |
| Reported to: | Internal IMR survey report, ICES, NAMMCO |

# Investigations on hydro-acoustic methodology

A Russian-Norwegian Workshop on “Improvement of instrumental methods for stock assessment of marine organisms” was held in Murmansk, 11-14 November 2003.

The main topics for the workshop were target strength investigations and combination of fish density estimates from acoustics and bottom trawl.

Research on survey methodology, involving comparisons between methods and standardisation of methods, should be continued.

# Norwegian – Russian Symposium

The 10th Norwegian – Russian symposium was held in Bergen, Norway, 27-29 August 2003, under the title “Management strategies for commercial marine species in northern ecosystems” and 50 representatives from scientific institutions, management authorities and fishing industry participated in it. Besides most important commercial species of the Barents Sea the symposium included also discussion of management strategies for relevant stocks in the waters of Faeroe Islands, Iceland, Greenland, Canada and Alaska, as well as approaches to ecosystem based management in different sea areas. The proceedings of the symposium will be published in the joint PINRO-IMR Report Series within March 2004.

The 11th Norwegian – Russian symposium will be held in Murmansk, Russia, in 2005, under the suggested topic: “Ecosystem dynamics and long term catch ambitions of the most important stocks in the Barents Sea”

# Catch volumes needed for investigations of marine resources and monitoring of the most important commercial species, as well as management tasks.

The agreed catch volumes shall satisfy the need for conducting all tasks described in “Joint Norwegian – Russian Scientific Research Program on Living Marine Resources in 2004”, included surveillance activities for the recommendation of area closures (and reopening of areas) as well as other decisions on management of fishing activities on living marine resources in ICES area I and II.

For these tasks, the following annual catch quantities are decided for each party in 2004:

- Maximum 18 000 tonnes of Northeast arctic cod.

- Maximum 3 000 tonnes Greenland halibut.

- Maximum 4 000 tonnes of other groundfish species, including bycatches.

For stocks harvested within a TAC, the catch quantities taken for these purposes are included in TAC (ref. Appendix 3 to the protocol from the 32nd session of the Joint Norwegian-Russian Fisheries Commission).

All catches for research- and management purposes shall be given separately in the catch statistics.

St. Petersburg, 14.11.03