## Computas AS
Appendix 7 Final Price | All costs in NOK excluded VAT/MVA
Date | 2009-10-21
Company Name | Computas
Exchange rate used
Currency used | NOK
Totals (Sum from tables 1 - 7 below) | Total contract value ex. Options | Total value of options | Total Cost used for price comparison
1: Total cost Optional services, Personnel cost pr hour | NA | 2925000 | 2925000
2: Total Cost Development / customisation of Use Cases | 36561245 | NA | 36561245
3: Total Cost Development / customisation of Options | NA | 9004849 | 7066463.95
4: Total Cost Software Components | 0 | 0 | 0
5: Total Cost HW 2011 | NA | NA | 3600000
6: Sum Optional services for Implementation (2011) and optional project cost | NA | 4932000 | 4041000
- | 19655989 | NA | 19655989
Grand Total | 56217234 | 16861849 | 73849697.95
Payment milestones | Contract Planned date (latest) | % of total contract value | Total payment in NOK
Payment for prototype and related software | 2009-12-15 | 10% | 5621723.4
Payments deliverables according to project plan | Total for all deliveries | 0% | 0
Detail spesification | 2010-02-01 | 20% | 11243446.8
Sprit demos 1 (defined in the spesification phase) | 2010-04-01 | 5% | 2810861.7
Sprit demos 2 (defined in the spesification phase) | 2010-06-01 | 5% | 2810861.7
Sprit demos 3 (defined in the spesification phase) | 2010-08-01 | 5% | 2810861.7
Sprit demos 4 (defined in the spesification phase) | 2010-10-01 | 5% | 2810861.7
Final Acceptance test | 2010-12-31 | 30% | 16865170.2
Final delivery | 2011-04-01 | 10% | 5621723.4
Guarantee period 1 | 2011-11-01 | 5% | 2810861.7
Guarantee period 2 | 2012-04-01 | 5% | 2810861.7
Total |  | 100% | 56217234
1: Optional services, Personnel cost pr hour | For extra services ordered by the Principal based on hours used (t&m), the following prices will apply:
Role | Cost pr hour Norwegian kroner (excluded VAT/MVA ) | Number of Hours used for price comparison | Cost used for price comparison
Project management in Oslo | 1200 | 500 | 600000
System specialist in Oslo | 1150 | 500 | 575000
Experienced SW-developer in Oslo | 1100 | 500 | 550000
System specialist at Contractors home office | 1200 | 500 | 600000
Experienced SW-developer at Contractors home office | 1200 | 500 | 600000
SW-developer | 950 | 0 | 0
Fucntional designer and usability experts | 1100 | 0 | 0
Test leader | 1100 | 0 | 0
1: Total cost Optional services, Personnel cost pr hour |  |  | 2925000
2: Development/customisation cost for Use Cases
Use case: | Development/ Customisation (Hours) | Your Overhead (Project management, inc. for instance specification, unit testing and deployment ++) (Hours) | Total hours per Use Case | Total cost per Use Case (NOK) | Probability of purchase (0-100%) Values less than 100% is an option to purchase | Cost used for price comparison | Hours required for customer involvement during spesification, development and testing.
UC 0.1 Definition of roles | 2006 | 401 | 2407 | 2611595 | 100% | 2611595 | 361
UC 0.2 Configuration of The Election System | 1747 | 350 | 2097 | 2275245 | 100% | 2275245 | 315
UC 0.3 Electoral Roll | 1177 | 236 | 1413 | 1533105 | 100% | 1533105 | 212
UC 0.4 Exception process for Electoral Roll | 941 | 188 | 1129 | 1224965 | 100% | 1224965 | 169
UC 1.2 Processing list proposals | 950 | 190 | 1140 | 1236900 | 100% | 1236900 | 171
UC 2.1 E-voting | 6250 | 1250 | 7500 | 8137500 | 100% | 8137500 | 1125
UC 3.1 Registration of p-votes in Electoral Roll | 1796 | 359 | 2155 | 2338175 | 100% | 2338175 | 323
UC 3.2 Manual registration of p-vote results | 990 | 198 | 1188 | 1288980 | 100% | 1288980 | 178
UC 3.4 Counting e-votes | 1337 | 268 | 1605 | 1741425 | 100% | 1741425 | 241
UC 3.5 Approval of p-votes and ballots | 493 | 97 | 590 | 640150 | 100% | 640150 | 89
UC 4.2 Settlement | 2019 | 404 | 2423 | 2628955 | 100% | 2628955 | 363
UC 5.1 Reporting | 2681 | 537 | 3218 | 3491530 | 100% | 3491530 | 482
UC 5.2 Auditing | 4253 | 851 | 5104 | 5537840 | 100% | 5537840 | 765
UC 9.1 Authentication | 1440 | 288 | 1728 | 1874880 | 100% | 1874880 | 259
2: Total Cost Development / customisation of Use Cases | 28080 | 5617 |  | 36561245 |  | 36561245 | 5053
3: Development/customisation of options
Use case: | Development/ Customisation (Hours) | Your Overhead (Project management, inc. for instance specification, unit testing and deployment ++) (Hours) | Total per option (Hours) | Total cost per option (NOK) | Probability of purchase (0-100%) Values less than 100% is an option to purchase | Cost used for price comparison | Hours required for customer involvement during spesification, development and testing.
Use Case: UC 1.1 Submission of list proposals | 1951 | 391 | 2342 | 2541070 | 70% | 1778749 | 351
Use Case: UC 3.3 Electronic counting of p-votes | 1537 | 308 | 1845 | 2001825 | 95% | 1901733.75 | 277
Use Case: UC 4.1 Reporting of results to SSB | 740 | 148 | 888 | 963480 | 95% | 915306 | 133
Requirement EIS5 The system shall interface with Altinn for the submission of list proposals (option). | Not provided | Not provided | Not provided | 0 | 50% | 0
Requirement OS 0.12B The Election System shall provide the e-voter with 'end-to-end' proof that the cast vote is received, recorded and counted as the voter intended. NOTE: To contract vote selling, this option may require a judicial process, where the confirmation that the vote is correctly counted is obtained in a controlled environment. | 2267 | 453.4 | 2720.4 | 2951634 | 80% | 2361307.2 | 408
Requirement OS 7.9 Where asymmetrical cryptographic private keys are shared as per OS7.7, they shall be generated using multiparty computation, so the private keys will not be known to anyone before they are to be used. For further reference see Realizing Distributed RSA Key Generation using VIFF (Mauland, Reistad & Mjølsnes 2009) | 420 | 84 | 504 | 546840 | 20% | 109368 | 76
3: Total Cost Development / customisation of Options |  |  |  | 9004849 |  | 7066463.95 | 8497
4: Software component cost | You must list all SW components we have to pay for
Name of component | Name of the component provider | Component cost 2011 pilots (If any) | Extra component costs for full implementation in Norway (If any) | Yearly maintenance cost 2012 - | Probability of purchase full implementation (0-100%) | Cost used for price comparison (2011 + full impl. + 5 year maintenance)
E-voting SW components
E-voting module (client and server) Open source | Computas | 0 | 0 | 0 | 70% | 0
|  | 0 | 0 | 0 | 70% | 0
|  | 0 | 0 | 0 | 70% | 0
|  | 0 | 0 | 0 | 70% | 0
|  | 0 | 0 | 0 | 70% | 0
|  | 0 | 0 | 0 | 70% | 0
E-counting SW components
Election Settlement Server open source | Computas | 0 | 0 | 0 | 80% | 0
E-Count | Opt2Vote |  |  | 0 | 80% | 0
|  | 0 | 0 | 0 | 80% | 0
|  | 0 | 0 | 0 | 80% | 0
|  | 0 | 0 | 0 | 80% | 0
|  | 0 | 0 | 0 | 80% | 0
|  | 0 | 0 | 0 | 80% | 0
Election administrative SW components
E-Roll open source | Computas | 0 | 0 | 0 | 95% | 0
EasyPrint | Opt2Vote |  |  |  | 95% | 0
|  | 0 | 0 | 0 | 95% | 0
|  | 0 | 0 | 0 | 95% | 0
|  | 0 | 0 | 0 | 95% | 0
|  | 0 | 0 | 0 | 95% | 0
|  | 0 | 0 | 0 | 95% | 0
Other required SW Components
OpenSSO (or functional equal) open source | Computas |  | 0 |  | 95% | 0
Glassfish appserver open source | Computas |  | 0 |  | 95% | 0
MySql open source | Computas |  | 0 |  | 95% | 0
|  |  | 0 |  | 95% | 0
|  | 0 | 0 | 0 | 95% | 0
|  | 0 | 0 | 0 | 95% | 0
|  | 0 | 0 | 0 | 95% | 0
|  | 0 | 0 | 0 | 95% | 0
4: Total Cost Software Components |  | 0 | 0 |  |  | 0
5: Hardware cost 2011 | Fill in the elements of the proposed solution in “Appendix 3 – Customer Technical Platform” for the elections in 2011. Costs incurred by the need for duplication of services in a hot standby site need not be specified, nor should network security or infrastructure be included in the pricing. The Tenderer has to cover own expenses for development environment and infrastructure and hardware cost related to their own development and testing.
Name of component | Description | Component cost | Quantity | Estimate (NOK) | Probability of purchase | Cost used for price comparison
Training |  | 300000 | 1 | 300000 | 0% | 300000
QA/Staging |  | 600000 | 1 | 600000 | 0% | 600000
Production |  | 600000 | 1 | 600000 | 0% | 600000
Basic 5 PCS Thales nShield connect 6000 |  | 1500000 | 1 | 1500000 | 0% | 1500000
Option Multiparty key generation 2 PCS Thales nShield connect 6000 |  | 600000 | 1 | 600000 | 0% | 600000
|  | 0 |  | 0 | 0% | 0
|  | 0 |  | 0 | 0% | 0
|  | 0 |  | 0 | 0% | 0
|  | 0 |  | 0 | 0% | 0
|  | 0 |  | 0 | 0% | 0
|  | 0 |  | 0 | 0% | 0
|  | 0 |  | 0 | 0% | 0
|  | 0 |  | 0 | 0% | 0
5: Total Cost HW 2011 | [5 empty] | 3600000
6: Optional services for Implementation (2011) and optional project cost | Based on your knowledge of our project and your experience, please make a estimate of the services for the implementation of the system in the pilot municipalities included the election in September 2011
Service Description | Description | Cost pr unit | Quantity | Cost | Probability of purchase | Cost used for price comparison
Cost of waiving the claims of reservations from standard agreement development(SSA-U) | Describe your reservations in SSA-U App 8 Changes to the General Contractual Wording |  |  | 0 | 95% | 0
Cost of waiving the claims of reservations from standard agreement mainteneance (SSA-V) | Describe your reservations in SSA-V App 8 Changes to the General Contractual Wording |  |  |  | 50% | 0
Cost of being paid in NOK rather than own currency | Currency risk, can be negative |  |  | 0 | 50% | 0
Cost of being paid in later than described (total contract sum) | % Pro Anno, 2months later payment |  |  | 0 | 50% | 0
Contractor Office cost in Oslo (if any) | Specify #persons in oslo |  |  | 0 | 50% | 0
Training , different course length, all preparation and documents included | Cost pr day, Principal cower facility cost | 19200 | 20 | 384000 | 95% | 364800
Deployment of solution to operating environment |  | 240000 | 1 | 240000 | 95% | 228000
System configuration per pilot |  | 72000 | 8 | 576000 | 30% | 172800
Preparation of scan centre(E-counting) pr scan centre |  | 120000 | 5 | 600000 | 50% | 300000
System Support e-counting (08:00-16:00 for one week). | 2. line telephone support |  |  | 48000 | 95% | 45600
System Support election administration (07:00-16:00 ) from 1.march to election day | 2. line telephone support |  |  | 1092000 | 95% | 1037400
System support e-voting 24Hrs/7days from July 1st to election day | 2. line telephone support |  |  | 1992000 | 95% | 1892400
6: Sum Optional services for Implementation (2011) and optional project cost |  |  |  | 4932000 |  | 4041000
7: Contractor project cost until September 2011 | Please present all the Contractor costs that are necessary to deliver a complete project in 2011. Give only the project cost not already specified in table 1-6 . The Tenderers core team must be located in Oslo, Norway, and all travel cost and cost related to presence in Oslo, if any, must be included in the tender.
Other project cost not included above | Description | Cost pr unit | Quantity | Cost | Probability of purchase | Cost used for price comparison
Cost of travel, accommodation |  | 10000 | 85 | 850000 | 100% | 850000
Contractor Security test |  | 286940 | 1 | 286940 | 100% | 286940
Contractor Performance and volume test |  | 102720 | 1 | 102720 | 100% | 102720
Contractor Usability and accessibility test |  | 1606814 | 1 | 1606814 | 100% | 1606814
Contractor System test (Fac. acc. Test) 4 man in 1 mth |  | 924480 | 1 | 924480 | 100% | 924480
Cost of development and test environment |  | 834550 | 1 | 834550 | 100% | 834550
Project management |  | 1085 | 7689 | 8342565 | 100% | 8342565
Documentation |  | 487240 | 1 | 487240 | 100% | 487240
Contractor Usability and accessibility req. |  | 1085 | 1248 | 1354080 | 100% | 1354080
Detailed common design ( 4 Man in 1 mth) |  | 1085 | 720 | 781200 | 100% | 781200
Certified Software (Specs and rules for programming) |  | 1085 | 120 | 130200 | 100% | 130200
Training course development |  | 0 | 1 | 0 | 100% | 0
Configuration and maintenance of environments (dev., test and system integration and test) including documentation fortraning, QA and production |  | 570000 | 1 | 570000 | 100% | 570000
Fault handling in Approval and guarantee period (3+12 mnths) |  | 1085 | 2400 | 2604000 | 100% | 2604000
Translations |  | 1085 | 360 | 390600 | 100% | 390600
Help texts translation |  | 1085 | 360 | 390600 | 100% | 390600
- | Diverse |  |  | 19655989 |  | 19655989
8: Other products and services offered | Based on your knowledge of our project and your experience, please describe and price other products and services that might be relevant for the Principal. These costs will not be counted in when evaluating Tender price.
Description of service | Description | Cost pr unit | Quantity | Cost per service | Probability of purchase
Digital Pen for List Proposal |  |  |  |  | ?%
Digital Pen Full Server Licence (Primary) |  |  |  |  | ?%
Digital Pen Full Server Licence (Redundancy) |  |  |  |  | ?%
Digital Pen - Client Access Licences |  |  |  |  | ?%
Voter Engagement Campaign |  |  |  |  | ?%
?%
?%
?%
?%
?%
8: Total Cost Optional services for Implementation (2011)